## Sheet1
Task | Start Date | Days to Complete
Literature Review | 2022-01-15 | 26
Design Planning | 2022-02-10 | 5
Computer Aided Design | 2022-02-15 | 28
Coding | 2022-02-25 | 28
Integrating Everything | 2022-03-20 | 10
Simulation | 2022-04-01 | 20
Making a Working Model | 2022-04-20 | 40
s